## Sheet1
Project Task
Meeting Room Booking System ¦ Mezbahul Islam
Task | Start Time | End Time | Remarks
Requirement Gathering | 23-11-2024 | 23-11-2024
Software Requirement Specification (SRS) | 24-11-2024 | 24-11-2024
Functonal Requirement Specification (FRS) | 25-11-2024 | 25-11-2024
User Interface (UI) | 26-11-2024 | 26-11-2024
WorkFlow | 27-11-2024 | 28-11-2024
Functional Requirement Implementation | 2024-02-12 | 2024-02-12
Core Functionality Implementation (Event Calendar) | 2024-03-12 | 2024-05-12
Database Design (ERD) | 2024-08-12 | 2024-09-12
Three Tier Architecture and Layout Designed | 2024-10-12 | 2024-10-12 | Project Implementation Started
CRUD for Room Facilities Management | 2024-11-12 | 2024-11-12
CRUD for Room Management (Include Facilities) | 2024-12-12 | 17-12-2024 | 12-12-2024 Not Complete(Facilities not included in Room) 15-12-2024 not complete. 17-12-2024 Room Management Complete.
Initialized Event Management Calendar | 17-12-2024 | 17-12-2024
Event Calendar Management: Select Event (Booking Create Started) | 18-12-2024 | 18-12-2024 | FrontEnd Done ( Modal Open while Select a date)
Event Calendar Management: Modal for Room Selection | 19-12-2024 | 19-12-2024 | Booking Created, Resources are taken in the leftside
Form for Room Booking and Event Click Booking Update Started) | 22-12-2024 | 22-12-2024 | Booking Update, Event BG color
Booking Managemnt Done | 23-12-2024 | 23-12-2024 | Booking Updated and Deleted
Meeting Create Validation Implementation (User Can not Book another meeting in the same time duration) | 24-12-2024 | 24-12-2024 | Some Basic Validation of Booking. Ex. no overlap booking. Booking BG Color, Minimum Booking 30 Minute.
Identity Framework: Authentication and Authorizaion (Role Create) User Sign up and Sign in Features | 24-12-2024 | 26-12-2024 | 24-12-2024 Authentication Done. 26-12-2024 Authorization Done
Admin Dashboard Management (Booking Request Accept/Reject) | 26-12-2024 | 28-12-2024 | 26.-12-2024 Accept/ Reject Functionalities are doing. Pending Bookings and Accepted Bookings are distinguished.
Resolving Front End issues | 29-12-2024 | 31-12-2024 | 31-12-2024 Date Time Issue Fixed and Alert issue Solved
User Dashboard Management (Booking Request Accept/Reject) | 2025-01-01 | 2025-02-01
Default Identity Entity Manipulation : Application User Create | 2025-05-01 | 2025-05-01
Some Improtant Features (Search, Sort, Pagination, Logger) | 2025-06-01 | 2025-08-01 | 06-01-2025 Search, Sort. 07-01-2025 Pagination.08-01-2025 Logging
All Functionality Test | 2025-09-01 | 2025-09-01
Presentation Prepared | 2025-11-01 | 2025-11-01
CSV bulk insert into the Database | 2025-12-01 | Continued
Manual User Create (Admin) | Continued | 15-01-2025 | Ajax form Submit
Delete Confirmation Popup | 16-01-2025 | 16-01-2025 | Custom Modal Added
Image Upload into the Meeting Room | 19-01-2025 | 20-01-2025 | Multiple Image Upload in Room
Meeting Room QR Code | 20-01-2025 | 21-01-2025